## General Planning
Release 1: Pure Asp.Net Mvc 5
Release | Tasks/Weeks | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
1 | MyTasks Modules | 17: Development
Portal/Core | bar: 17 to 21
Project Module | bar: 22
User Administration | bar: 23 to 24
Ticket Module | bar: 25 to 27
DashBoard | bar: 28 to 30
Reporting
Release 2: Moving Ticket to Angular 2
Release 3: Create Android and iOs version with Xamarin
Note on G3: Autor: Domingo 22 Mayo
Note on T3: DeadLine: Domingo 21 Agosto
Note on G5: Domingo 22 Mayo
Note on H6: Domingo 29 Mayo
Note on J7: Domingo 12 Junio
Note on M8: Domingo 3 julio
Note on P9: Domingo 24 julio
Note on S10: Domingo 14 Agosto

## PortalAndCore
Portal Core Tasks | Is Ready | Description | Estimado
Error handling | ok | Using elmah support
Localization support | ok
Database Update System | ok
Setup Module (Db update) | ok
SysteSetting Module | ok
BugReporting | ok

## Project Module
Category | Is Ready | Description
Db | ok
Backend | ok
UI | ok
Validation | ok
Localization | ok

## User Administration
Task | IS Ready | Description
Add,edit and list | yes
Localization | yes
Implement sending mails after create users | yes
Implement forgot password | yes
Implement activation user usigng mail | yes

## Ticket Creation
Task | Is Ready | Description
Localization | yes
Validations | yes
Add Upload Files Features | yes

## Ticket List
Task | Is Ready | Description
Filter creation
Sorting
Pagination

## Ticket Editions
Task | Is Ready | Description
no
no
no

## Edit Profile
Task | Is Ready | Description
no
no
no

## DashBoard
DashBoard Tasks | Is Ready | Description | Estimado
UI | no |  | 3w
BackEnd | no |  | 2w

## TickeModule to NG2
Ticket Tasks | Is Ready | Description | Estimado
Learning Angular 2 |  |  | 2w
Change Ticket UI Creation to NG2 | no |  | 2w
Change to Db | no |  | 1w
Change Ticket List to NG2 | no |  | 2w